Designing and Developing a System Under Pressure
Or
”How to do software right even
        in challenging environments...”
Advanced Software Engineering 475
Andrew McVeigh

---
Building a Commercial System
- At uni we are told how to build applications
- We learn about:
  - Gathering requirements
  - Programming, design patterns
  - Architectures and different styles
  - Different methodologies: agile, test-driven, iterative...
  - Different modelling approaches: UML, statecharts...
  And it's all very good
  BUT
  How do you apply these techniques under commercial pressure?

---
Under Pressure
- Clients and changing requirements
  ”I've changed my mind. Here are my new ideas”
  ”Make it completely generic to cope with all future requirements”
  ”We want it cheaper, delivered faster and better”
- Nasty clients who view you as inferior
  ”Deliver this or you are out of this job. It's easy, a kid could do it”
- Uncaring and ignorant managers
  ”We want it now. Stop telling me about problems and just do it”
  ”I know we don't have the requirements, just finish the design”
  ”I don't know where the devices are that you need to do the work”
- Managers under pressure themselves
  ”You are going to have to work all hours to make this delivery”
- Cowboy coworkers
  ”I didn't understand so I hacked the fix in. I didn't make any tests”

---
So What Happens
- Some projects prosper under pressure
  - Systems developed under great pressure that are still around
  - Architectures with strong themes that have been ”handed around” and still kept their structure
  - High morale and a team culture that supports developers
  - A business that ”buys into” the vision that gives wage increases
- Some projects fold under pressure
  - Systems delivered late or never at all: lots of money wasted
  - Unmaintainable systems that are being continually rewritten
  - High turnover of staff from poor morale; no ”team bonding”
  - Stress causing sickness: hospital visits in extreme cases
    (Unfortunately, I'm not joking about this. It happens)

---
What Are The Differentiators?
- Why do some projects do well and others badly
  - What causes pressure to help some projects and harm others?
  - What are some signs of project failure and ways to move it in a positive direction
- It often depends on the reaction to pressure...
- This is an ”attempt” at a set of guidelines for different situations
  - Ways to approach different aspects of making software
  - Coping strategies for pressure and badness
  - How to normalise the situation and move towards goodness
  - How to avoid the common pitfalls: signs to look for
  - Retaining professional integrity (and character) under pressure
  - Perhaps most applicable to large systems

---
Case Studies
- Case D: Deathmarch
  - £100m system; complete rewrite of a large business suite
  - Financial applications
  - Complete failure, multi-year programme delivered no value
  - Outsourcing, insource, consultants, famous names
  - CEO fired from prestigious role
  - More common than you think
- Case S: Surprisingly successful
  - £30m initial system; new business system developed over 3 years
  - Smartcard issuance and personalisation system
  - Started badly initially; people left under little direction
  - Finally: 12 week delivery period under great contract pressure
  - Still being developed, maintained and sold after 10 years

---
Work To A Methodology...
(it actually helps)

---
What is a Method(ology)?
An approach to structuring, planning and controlling the development of software
http://www.cms.hhs.gov/SystemLifecycleFramework/Downloads/SelectingDevelopmentApproach.pdf
http://en.wikipedia.org/wiki/Software_development_methodology
- These are the general guidelines that determine:
  - How and when you gather requirements
  - What documentation needs to be produced
  - How you plan releases: when and how often
  - How you do system and acceptance testing
- Lots of variability in processes:
  - Iterative and incremental versus waterfall
  - Lots of ceremony (documents etc) versus little
  - Prescriptive (defence + critical systems) versus descriptive

---
Modern: Iterative and Incremental
Follow a set of steps to deliver iteratively
Gather
requirements
What do
they want?
Iteration #1
Do some
design
How are we
doing to do it?
Develop
Time
Iteration #2
Gather
requirements
Let's code it
Let's code it
Do some
design
Integrate and
System test
Let's check it against
the requirements
Develop
Deliver iteration #1
etc...

---
Mistake #1: No Methodology
- AKA: Throw smart people together into a room...
  ”They'll work it out together, they're smart enough”
- This happend on project S
  - After 6mths of little progress, no progress → disaster looming
  - Lots of people left due to stress and disorganisation
- Finally, roles and a light process were introduced
  - People hired who knew how to organise others → managers
  - People hired who knew how to structure large systems so lots of people can work on it at once
  - Lucky escape?

---
Mistake #2: Too Much Ceremony
- 2 big issues
  - Too many documents to produce, too many steps to follow
  - Too ”waterfall”: no iterations
Produce 300 page document describin
everything down to screenshots of GUI
requirements
design
Produce full design of system
With lots of line and box diagrams
Code quickly because everything
is known
code
Integrate &
test
Test this and release it
What if something goes wrong?
How can you design all up front?

---
Mistake #3: The Silver Bullet
- Methods can hide lack of competence
  - People look like they are doing work
  - But they are just following steps and shuffling paper
  - The method becomes the boss...
  - System D did this
    (Lots of ex-Cobol programmers trained for OO and RUP)
- A method is not a silver bullet!
  - It cannot kill the ”werewolf” of software
  - A method does not guarantee success
  - Lack of a method does not guarantee failure
  - But... as a project gets bigger, processes are needed

---
My Preferred Approach
- Follow a process
  - Studies show that a process is usually better than none at al
  - Push to move towards iterative
- But...
  - Keep it light and not too prescriptive
    (avoid making documents that are not required)
    (a process must help, not hinder)
  - Prefer early and iterative development
    (i.e. delivery quickly and build on this in a principled way)
  - Tailor the process for the environment
  - Look for a standard way of documenting requirements and design

---
Some Common Sense
- Requirements:
  - Work out what is required for the deliverable
  - Work with the clients/customers/business
  - Document this: find a way to communicate this to stakeholders
    (stories, use cases)
  - Expect changes, be flexible → more on this later
- Design & code usually interact
  - You will be sometimes asked to design/code before requrements!
    → if so, make your own requirements and document them
  - Do some design, don't expect code to magically be well designed
  - Design and coding often go hand in hand
- Sometimes high ceremony is actually useful
  - Military / space / telecomms / critical systems. CMM5 etc...

---
Interesting Waterfall Survival Technique
- Sometimes people will force waterfall on you
  - You can fake an iterative process within this
  - This is the way the Booch process used to actually work
requirements
design
code
Integrate &
test

---
Requirements and Analysis
Understanding and agreeing
the problem to solve

---
What is Expected of the System?
- Find a way to describe this in terms stakeholders understand
  - Describe the operation of the system from a user's perspective
Smart card system
(1) User requests
new card
(2) system builds applications
(3) system gathers data
(4) system loads apps
onto card

---
Good Requirements Practice: Listen and Filter
- Make sure you actually gather requirements!
- Listen to the users
  - If they are experts in the domain, listen especially carefully
  - Don't try to be too clever: listen and replay back
- However, don't give them everything...
  - Filter out silly stuff or things that are not helpful
  - Work out what is essential versus what is cosmetic
- Expect requirements to change
  - Look for a core that is common despite change
  - Listen carefully to the language of the users, this is unlikely to change particularly if they are experts in the domain...

---
”Make me a generic system”
- ie. We want this software to clear all financial products
  - The problem is, unless we are experts, we don't know if it can
  - The very idea, though, is often attractive to business people
- Be very careful when you hear the word ”generic”
  - Even seriously good domain experts cannot predict the future
  - Test any requirements by making them concrete
    - i.e. We will clear a swap using the generic process in the following way
    - i.e. We will clear a repo using the generic process in the following way...
- Too often ”generic” is a synonym for
  ”it can't be that hard” or
  ”everything is really just the same thing”
  → i.e. the wish for a silver bullet that will take away all IT problems

---
Analysis
- Forming a conceptual model of the system
- Find a comfortable way to express this
  - For me, it is UML
  - Walk through the steps of the requirements with the analysis model
- Tip: If you cannot describe it, you cannot build it
(1) get cardholder details
request
cardholder
(2) build an application
using the data
(4) load it onto the card
application
smartcard
delivery
channel
(3) package it with card security data

---
Pitfalls
- Trying to specify the entire system all at once
  - Do it in iterations: ”here are the requirements for iteration #1”
- Getting no requirements
  - Can we create a system without sharing a common view on what it does?
- Doing too much analysis
  - ”Analysis paralysis” is suprisingly common
  - Do just enough analysis and move onto designing and coding
- Doing no analysis
  - Analysis helps clarify the situation, may even affect requirements
- Not listening to the language of the domain experts

---
Designing the System
Agreeing on common
concepts and structure

---
What is Design?
- My opinionated view:
  - It's an elaboration of the analysis model
  - Make packages for each of the major concepts and then think about what is needed in each of the packages
  - Use interfaces for major design concepts

---
Pitfalls
- Doing too much up front design
  - Design and coding are synergistic activities
  - Too much design prevents the start of coding which might show flaws in the design
  - Spend maybe a few days to a week to understand the structure
- Doing no up front design
  - Can we create a system without sharing a common view on how it is structured? Not if it is large...
  - ”No design” approach can work if the team is small and work together very closely
  - Otherwise, look to ”get onto the same page”
  - Push back if management say ”just code this up”

---
Pitfalls (2)
- Not approaching the design as a team
  - Involve others, brainstorm, listen to comments carefully
  - Try to agree as a team
  - Involve senior and junior developers
  - Develop a common language for the domain and design approaches
- Doing the design as a paperwork exercise
  - i.e. we are doing this to tick the box that says ”design”
  - Push back on this, unless on a critical system
  - Make design appropriate for the task at hand
- Too much design by pattern
  - Quite common at one point: ”we have a composite here and a singleton here...”. Patterns aren't meant to be used like this!

---
Coding the System
The fun bit...
but you must do
automated unit testing

---
And then onto coding...
- This is the fun bit generally: a teambuilding exercise
  But, ensure that you write automated unit tests
  ”Programmers who don't write unit tests are not professional”
  - Adopt a test-driven approach if possible
  - Treat the tests as part of the codebase
  - Learn techniques for unit testing in complex situations
    (e.g. with databases, http etc)
  - Measure your coverage
  - Think about what and why you are unit testing
    ”Unit testing is your friend. They let you refactor and fix breakages. Static typing is not enough”

---
Unit Testing: A Personal Account
- It's easy even for old programmers like me:
  - Several years ago
    - No real unit testing, I knew I needed it but...
    - Too much work to make and maintain tests?
    - It seems to take much of the fun out of coding...
- I've managed to incorporate unit tests into my programming ”rhythm”
My old way
My new way
Write some code
Same effort
Write some code
Write tests
and verify
Manually test and verify
Change some existing code
Change some existing code
Less effort!
Manually test a bit
and hope for the best...
Rerun tests and maybe
write a few more...

---
Unit Testing (2)
- What if you work on a legacy system without unit tests
  - Start making them now!
  - Integrate the creation of these into programming practice
  - Start measuring coverage and working out how to improve it
  - Work at testability... interfaces really help here
  - Treat it as a learning exercise:
    introducing modern practices into old software
- What if a co-worker won't unit test??
  - Write some tests and educate them (or shame them ;-)
  - Ask for it to be included as a daily build report
  - Mention it to management if they don't listen...
- As for me:
  - I will not employ someone who doesn't unit test
  - I always ask questions in the interviews about unit testing and testability techniques: i.e. Avoidance of singletons etc.

---
Delivering Quickly Without Compromise
Horizontal and Vertical Slices

---
Getting Results Quickly
- The challenge: getting tangible results quickly
  - Establishes a baseline system, rather than just bits
  - Gives confidence in the system to management
  - Builds up momentum for the next iterations
  - Prevents the project from being cancelled!
- So, how do we get results without compromising on:
  - The structure and design of the system?
  - Testing of the system?
  - The hours we work? (i.e. Let's not kill ourselves and have no life)
  - The long-term quality of the code?
    ANSWER: a vertical slice!

---
A Vertical Slice is an End-to-End Story
- E.g. The delivery of a single application onto 1 card
  - Might be very ”thin” functionality but it is end-to-end
  - Demonstrates a complete story
  - We can build out the functionality later (horizontal slices)
(1) request via
web interface
(3) load it onto a card
via the web
(2) build small app

---
Vertical versus Horizontal
System
request
Iteration #1
End-to-end
delivery
cardholder
Vertical →
Features needed
for a story or
use case
application
smartcard
delivery
Horizontal →
Richness of function and options

---
What About Cutting Corners?
request
An expedient
Implementation?
i.e. No real security?
Use interfaces!
cardholder
application
smartcard
delivery

---
Keeping Expediency Segregated...
- Use interfaces to separate components
  - Expedient code should not mingle with real code...
  - Use horizontal slice in an iteration to fill out over time
request
cardholder
application
smartcard
delivery
channel

---
Iteration #2: Real Application Security
request
Security subsystem
added to application
layer
cardholder
application
smartcard
delivery

---
Slices
- Use vertical and horizontal slices to plan iterations
  - Vertical to get results, built momentum
  - Vertical to test architecture, verify design
  - Horizontal to bulk out functionality
  - Horizontal gets filled out as we do more vertical cases
- Use interfaces between components
  - Allows us to segregate expedient and production-ready code
  - Builds up a design and an architecture for us
  - Interfaces should correspond back to analysis model in some way

---
Iterating Forwards
Keeping up momentum

---
We Have Momentum...
- We've delivered a vertical slice
- We've worked hard and have delivered
  - Management are happy, people are smiling again...
  - But we can't keep going at this pace forever
  How do we sustain and ”nurture” our momentum?
- Tips:
  - Have some level of organisation: Timeboxing and DSDM
  - Manage expectations to avoid overwork and burnout

---
Timeboxes: Gently Pressuring
- Strange observation:
  ”A programmer will often take twice as long to do a task as they estimate”
  So, we take the programmer's estimate, double it and put it on a plan
  … but then they take double that!
- This is a bit harsh
  - But, I've noticed it in myself
  - As timescales get longer, I relax and avoid too much hard work
- Timeboxing lets us avoid this odd dilemma
  - Keeps gentle pressure on people
  - Lets them work to their own estimates

---
Timeboxes: Spring Loaded
- Bob estimates that:
  - Task A, B, C, D will each take 1 week
- Our iteration is 3 weeks
  - MoSCoW classification
  - Task A is a ”must”, B is a ”must”, C is a ”should” and D is a ”could”
The team timebox..
Bob's work:
Task A
Task B
Task C
Task D
...
Jill's work:
Task Q
Musts can only take 50% of the timebox time → These definitely must be done
Bob ”should” also do the shoulds... We shouldn't really take 2x as long as estimated
If he has time and is super-productive, Bob might also finish the ”coulds” and ”woulds”

---
Timeboxes: Why They Work...
- Musts are never more than 40-50%
  - These must get finished or the timebox is deemed to have failed
  - The team doesn't want this generally...
  - But, based on the estimates, the 2x effect is ok as long as the musts get done
- But, seeing the other tasks makes us go faster
  - We ”should” really get the musts finished and move to the shoulds
  - Gives people a chance to show how productive they are
- General rule:
  - People will try really, really hard to make an achievable deadline
  - They will give up for something unachievable...

---
Some Tips
- Must 50%, Should 25%, Could 15%, Would 10%
- If you are the team lead
  - Have a private word with non-performers
  - Avoid embarrassing people in front of the team
  - They may have reasons for not getting the work done
    But...
  - be fair and firm → pressure those not delivering
  - Use historical data to get more accurate estimates
  - Some people underestimate constantly
  - Some people give silly estimates to make their lives easy

---
Some Tips (2)
- Manage the client's expectations
  - Don't ”promise the earth”
  - Don't underestimate or cut estimates just because...
  - Clearly articulate what each iteration will deliver
  - But have an end-state vision of the system to work towards
- My own personal bug-bear
  - Never show a finished or polished interface for an early iteration
  - It gives the appearance that the project is nearing completion
  - Don't make it look amateurish, but put in obviously unfinished bits
    - i.e. Stock images, incomplete graphics etc.

---
If You Get To Be A Team Lead...
- Read this book. It shows how to:
  - Take on an existing project
  - Handle non-performers
  - How to manage expectations and motivate the team
Leading a Software Development Team:
A Developer's Guide to Successfully
Leading People and Projects
Richard Whitehead
(I really wish I'd had a book like this in the
 early part of my career...
I learnt a lot the hard way)
Disclaimer: I just like the book, I don't know
the author...

---
Developing an Architecture
Structure and themes that
everyone understands

---
The Full Vision and System Structure
- Ensure that people know what the entire system looks like
  - So they will know how their bit fits into the system
  - Should be simple enough to show the business / client
  - Everyone should buy into this
  - Establishes a common vocabulary and terminology

---
An Example from Nat...

---
Architectural Pitfalls
- Making the system too complex
  - Why does it have to be difficult? To justify the architect's job?
- Reliance on complex technologies
  - At the core, it should just be objects without coupling to EJBs or complex middleware or databases
  - Use Nat's ports and adapters pattern to do this well:
    http://www.mockobjects.com/book/object-oriented-style.html
    http://natpryce.com/articles/000772.html
  - Or buy (or download ;-) his excellent book:
    ”Growing Object-Oriented Software Guided By Tests”
    Freeman and Pryce...
    - Lots of good advice in there...

---
Project D Case Study:
A ”Generic” Financial System
Flawed in principle...

---
A Completely Generic System
- The goal was to create a completely generic financial system
  - Very large project with 100+ people
  - Aim to revolutionise the business
- Way too ambitious
  - This type of genericity is more or less unachievable...
  - Retraining all the old COBOL programmers in OO techniques
  - Outsourcing to consultancies, famous names
  - The vision was sold by a consultancy: conflicting interests
- I joined as a consultant in the .com crash era
  - Started as a requirements analyst
  - I ended up responsible for one third of the technical delivery

---
Early Mistakes...
- Requirements were almost impossible to get
  - Even the experts couldn't describe what they wanted properly
  - Too generic, nothing concrete
  - Unskilled analysts
- ”Just design without requirements, they'll come later”
  - We were actually told this
  - Clear sign something is not right
  - Alarmingly, the manager who said this thought it made sense...
- Eventually, lack of progress was noticed...
  - Timescales put in place to force progress
  - Didn't help... Now shortcuts were being taken...

---
Early Delivery
- Requirements were produced
  - Less than adequate
  - Design went ”meta”
    - i.e. A meta-model to cope with the genericity
- Delivery date passed
  - A subset of the project delivered on time
  - Kept the board and CEO happy for the interim...
    BUT
- This was a smokescreen for larger problems
  - Poor, incomplete requirements
  - Muddled implementation

---
What Happened Eventually?
- After 3 years project was cancelled
  - Written off for taxation reasons
  - No value delivered
  - Prominent CEO removed from post
  - Legacy systems are still being used
- What should have happened
  - Existing management should have examined promised more closely...
  - They were bamboozled by the promise of a generic system
  - The approach was flawed in principle
  - The head of the new system was arrogant and disregarded the existing systems completely
    - anyone associated with these was left out...

---
What Did I Do?
- Went back to principles:
  - Requirements documents and sensible approach
  - Lightweight design
  - Iterative delivery
  - Spotted poor performers and removed them
- But: it was a deathmarch
  - Planned to get out
  - Left a year before it collapsed
  - In retrospect I should have left earlier: did I partially prop it up?
  - Reflection: what could I have done better?
  - Reflection: I needed the job?

---
Conclusion
- Some projects cannot be saved and must be let to die quickly...
  - Duty to notify management if they will listen
- Rewrites usually suffer from 2nd system effect
  http://en.wikipedia.org/wiki/Second-system_effect
  - Be careful when rewriting. Mozilla also found out the hard way
    http://www.joelonsoftware.com/articles/fog0000000069.html
  - Better to refresh a system incrementally rather than completely rewriting. A harsh lesson.
  - We need to discuss project failures more openly. This is not an isolated type of incident:
    http://www.cis.gsu.edu/~mmoore/CIS3300/handouts/SciAmSept1994.html
    http://news.bbc.co.uk/1/hi/uk_politics/8397854.stm
    CSA, FBI case worker system, the list goes on and on...

---
Project S Case Study:
A SmartCard Issuance System
”Generic done better”

---
The Situation
- Company won a multi-million £ contract
  - Write a smartcard system for a large card company
  - Great name visibility, but contract will lose money
  - So, write it generic so we can reuse it...
- I arrived 6 mths after the contract awarded
  - Disarray: lots of smart people doing nothing, morale low
  - Little progress
  - Card company notices and issues ultimatum:
    ”Deliver a working system in 12 weeks or...
    contract is cancelled”.
  - System architect leaves... Whoops.
  - What are we going to do?

---
A Great Opportunity
- Sometimes pressure provides an opportunity
  - Everyone who was interfering went hands off
    - Noone wants to be associated with a failure
  - Chief architect leaving == noone to tell us what to do
- So, we go back to principles
  - Luckily they had excellent requirements from very good people
  - We then analysed the requirements to form an analysis model
  - Structure builds around the model
  - We apply iterative techniques for the first release
- 12 weeks is just enough to build a few vertical slices...

---
But It Still Has To Be Generic...
- We take a different approach
  - We have a single customer!
  - We build it concretely for the customer
  - We have a good attempt at putting in interfaces to make it reusable
  - We use domain experts to tell us how it should look...
  - Will the approach pay off?
- 12 weeks later we have a system which can
  - Deliver smartcard applications via the web
  - Client likes it and backs off...
  - Now the fun really begins...

---
The Parasites Come Back...
- Now that the project is back on track we get
  - The managers and other people who went ”hands off” coming back to claim ownership
  - People coming back with crazy requirements and timelines
  - The CTO suggesting we are just making a prototype
    - He will staff a team to do the proper version
- Solution: politics
  - We spent time cultivating influence with the CEO and important technical managers
  - They agreed to let us make the real system and we explained the vertical slice concept
  - We were elevated to prominent positions: this can be how it happens

---
Timeboxing
- We used DSDM and timeboxing techniques
  - Great pressure, these helped level out the effort curves
  - 40 hrs a week pretty standard
  - Iterations planned out and executed well
  - Customer happy
- We built out the generic system
  - Built to interfaces
  - Used an architecture to communicate how the system worked
  - Tried it on other customers
  - It worked, company made money
  - System still being sold and maintained years later

---
Conclusions
- Go back to basics and engineering principles
  - They really do work
  - Iterate: collect requirements, analyse and design and code
  - Have a structure where people know what is expected
- But
  - New batch of requirements came in; didn't make sense
  - We worked to refine them and rescued that too...
  - Be vigilant... Good things can go bad

---
An Engineering Outlook
Learning to avoid
being a hero...

---
An Engineering Approach...
- Avoid being essential
  - Unless you want this → some do, but it's not a great way to live...
  - If you are essential, you will get stuck in 1 area
  - Being essential required a certain level of ”emotional blackmail”
- 2 ways to avoid being essential
  (A) Do poor work or avoid responsibility → bad
  (B) Work in a principled way
  - Document what you do, and arrange to handover
  - Manage upwards
  - Give credit to other team members
  - Management actually prefer this... and reward it

---
Some Stereotypes
- ”The Hero”
  - Working all hours to make deadlines
  - Overpromise
  - Enjoying things failing, so they can rescue it
  - Enjoy the buzz of not testing
  - Thriving in chaos
- The alternative:
  - Plan realistically and manage expectations
  - Aim for 40 hours a week
  - Rigorously test and adopt best practices
  - Look for process improvements

---
Some Stereotypes (2)
- ”The Grump”
  - The language I know is the only one I care about
  - Anything that I don't know is not good
  - I won't bother to learn anything new, it has no value
  - … even if I'm asked to do so...
- The alternative:
  - Continuous learning
  - The more you learn the easier it becomes, as you build on foundations
  - People will actually pay you to learn new technologies!

---
Some Stereotypes (3)
The ”Know it all”

---
My Experience
- Running a small team
  - 4 developers + 1 manager
  - Duty of care towards the team
  - Expect great engineering, prepared to reward great engineering
- Developer A:
  - Great initiative in writing unit tests
- Developer B:
  - Superb engineering approach: tests, documentation, timelines
- Team leader:
  - Difficult initially, needed to learn the ”ropes”
- Me: I worked myself out of a role... but I left upwards...
  - In meetings, I just described how great the team's approach was...

---
Common Non-Technical Pitfalls
How to recognise these
and cope

---
Burnout
- Avoid more than 50 hrs a week
  - It can't be done forever
  - It's a sign of bad planning, poor expectations etc.
  - Efficiency goes down quickly
- My early experiences: a breakdown
  - It's not unusual: hospital visits from the trade floor
- The solution:
  - Take a step back – leave the situation
  - You are never as essential as you think
  - Take regular time off and look for symptoms of burnout
  - Don't work weekends if possible

---
Politics
- People like to take sides and play political games
  - People want to build power bases
  - They may ”badmouth” others to do this
  - They may form ”tribes” and fight by withholding resources etc.
- The truth:
  - Politics is unavoidable: align yourself politically
  - Avoid games and backstabbing: keep your integrity
  - Software delivery is never served by politics
  - Avoid the games when you rise through the ranks...
- A tip:
  - When working for a consultancy you have 2 masters
  - Be honest and upfront with the client
  - Easy to always toe the consultancy line... but beware...

---
Coping with Poor Managers...
- Some common issues:
  - Clueless managers who expect the ”world”
  - Non-technical managers managing IT
  - Lazy managers who expect you to work hard
  - Managers who don't provide you with the right materials
- Some coping tactics:
  - Be professional, but promote yourself to the manager
  - Avoid badmouthing colleagues: you are all in this together
  - Cultivate associations outside of your team
    - Let others know of your achievements
  - Learn to ask the right questions
    - i.e. Clarify expectations
  - Avoid the situation when you want to fail to make the manager fail

---
The Job Curve
Many jobs start like this...
2-3 months
They think you
are good...
They think you
are not good...
Time in job

---
A Deathmarch
- Some IT projects are doomed: the ”deathmarch”
  - They are too ambitious and too risky
  - They have incompetent people running them
  - They are going to crash and burn
    OR
  - They are going to cause you to spend years of pain achieving little
- Planning to leave
  - Sometimes you just need to get out of a bad situation
  - Never leave a job before you have got another
    (easier to find a job when you already have one)
  - Watch for the warning signs → you'll know when it happens
    - Crazy plans, crazy hours
    - No hope of the project working technically
    - Incompetent managers

---
Summary
- When faced with pressure, go back to your training
  - Gather requirements to know what is wanted
  - Analyse to understand the problem better
  - Design to give a system structure
  - Code like an engineer: unit tests and a principled approach
  - Don't become indispensible
  - Manage yourself ”up and out” if possible
- Manage your career
  - Keep up continuous learning
  - Promote and manage upwards so they know you are good
  - Watch for burnout and ease off: be gentle on yourself
  - Plan to get out if it is intolerable: an engineering approach

---
Random Points (1): Programming
- Keep your programming skills
  - Like writing
  - Finding your voice
- But

---
Random Points (2): Look up
Don't program all the time

---
Random point (3): Opportunities
- Golden age
  - People say the golden age has passed – don't believe it
  - I've seen this happen maybe 5 times...
  - Ageism?

---
Random point (4): Be Open
- Opportunities only look clear in hindsight
  - Client-server + rise of SQL
  - Internet + dot-com
  - Mobile phones
  - Open source + linux
  - Online advertising
  - Search
  - Ebay, Google, Craigslist, Facebook, Napster, Youtube, Thawte
  - Iphone apps, XML, Java, AJAX + Web2.0, Ruby on Rails
- Very easy to miss: they only look clear in hindsight
  - Apple + internet: ”what on earth was that about?”
- Negatives are really opportunities
  - Outsourcing
  - .com crash
  - Death of Pcs
  - Funny story about ”latest one”